## Test cases
Product Name |  |  | https://www.zappos.com/ | TC start date | 2023-12-07 | TC Execution Start Date | 20/7/2023 | TEST CASES |  | List of the emprovement Scope
Module Name |  |  | User Management web page | TC End date | 18/07/2023 | TC Execution End Date | 30/07/2023 | PASS | 59 | Name field should take valid formate
Developer Name |  |  | Mr.XX | Test Case Developed By | Ramisa Anan |  |  | FAIL | 8 | System should be sent OTP code
|  |  |  | Test Case Reviewed By | N/A | Performance (tested) |  | Not Executed | 0 | Marchent corner Password field must be Improve
Test Executed By |  |  | Ramisa Anan
[8 empty] | TOTAL | 67
Test Case ID | Module | Feature | Test Case | Test Steps | Test Data | Expected Result | Actual Result | Bug Screenshots | Status | Remarks
TC001 | Zappos web Page | Registration | Verifying whether the Registration page appears | 1. Go to url "https://www.zappos.com/" 2. Go to "login" menu and click on register section 3. A new page appears with having Register andregistrationbuttons. Click on the "Register" button. | N/A | A registration UI should apear | Registration page show properly |  | Passed
TC002 |  |  | Check the my account section and select to create new account page. | 1. Go to url "https://www.zappos.com/" 2. Go to "My account" menu and click on register section. | N/A | The expected my account page should be shown in all sections. | Check to my account inpute blank at first show error massage and registration page |  | Failed
TC003 |  |  | Try to registration in without Name/Email/Phone Number and Password | 1. Browse the URL (https://www.zappos.com/) 2. Keep the Email box and password blank 3. Click on the Register button | Name/Email/Phone: number = Null Password = Null | User should not be able to registration and there should be an alert such as "Please enter Name,email or phone number" | Not able to registration and the alert message shows properly |  | Passed
TC004 |  |  | Try to register without Name/Email/Phone Number with Password value | 1. Browse the URL (https://www.zappos.com/) 2. Keep the Email box blank and put valid password 3. Click on the Register button | Name/Email/Phone number = Null Password = acD@585197 | User should not be able to registration and there should be an alert such as "Please enter valid email or phone number" | Not able to registration and the alert message shows properly |  | Passed
TC005 |  |  | Try to registration with valid Email but empty Password | 1. Browse the URL ("https://www.zappos.com/") 2. Put the valid Email in the box and keep password empty 3. Click on the Register button | Email = ram***@gmail.com Password = Null | User should not be able to registration and there should be an alert such as "Please enter password" | Not able to registration and the alert message shows properly |  | Passed
TC006 |  |  | Try to registration without Name valid Phone Number with a valid Password | 1. Browse the URL ("https://www.zappos.com/") 2. Put the valid Email and password in the box and keepName empty 3. Click on the Register button | Name: Null Phone:01856*******16 Password:12345 | User should not be able to registration and there should be an alert such as "Please enter Name" | Not able to registration and the alert message shows properly |  | passed
TC007 |  |  | Try to registration in name field with numeric value | 1. Browse the URL ("https://www.zappos.com/") 2. Put the name in numeric value 3. Click on the Register button | Name:8765899897 | User should not be able to registration and there should be an alert such as "Please enter Proper Name" | able to registration |  | Failed
TC008 |  |  | Try to registration Phone number value in alphabet | 1. Browse the URL ("https://www.zappos.com/") 2. Put the field in letter 3. Click on the Register button | Name:Ramisa Anan Phone:dfkkdjfkdffkgjgkjgj Password:04123456 | User should not be able to registration and there should be an alert such as "Please enter Proper Name" | Not able to registration and the alert message shows properly |  | Passed
TC009 |  |  | Try to registration Phone field with special characters | 1. Browse the URL ("https://www.zappos.com/") 2. Put the field with special carecter 3. Click on the Register button | Name:Ramisa Anan Phone:&#$@*&%$#@ Password:7342345 Retype Pasword: 041234 | User should not be able to registration and there should be an alert such as "Please enter Proper Name" | Not able to registration and the alert message shows properly |  | Passed
TC010 |  |  | Try to registration without retype password | 1. Browse the url ("https://www.zappos.com/") 2. Click on "login" button. 3. A new page will appear having Registration In and registration button. Click on "Registration" button | Name:Ramisa Anan Phone:0182228**14 Password:6422345 Retype Pasword: Null | User should not be able to registration and there should be an alert such as "Please fill retype password" | Not able to registration and the alert message shows properly |  | Passed
TC011 |  |  | Try to Registration Phone field with alpha-numeric input | 1. Browse the URL ("https://www.zappos.com/") 2. Put the phone field with alpha-numeric 3. Click on the Register butto | Phone: Ramisa Anan98765 | User should not be able to registration and there should be an alert such as "Please fill retype password" | Not able to registration and the alert message shows properly |  | Passed
TC012 |  |  | Try to registration Phone number field with up 10 digits | 1. Browse the URL ("https://www.zappos.com/") 2. Put the number 4. Click on the Registration button | Phone:0193456781 | User should not be able to registration and there should be an alert such as "Please fill retype phone number" | Not able to registration and the alert message shows properly |  | Passed
TC013 |  |  | Try to registration Phone number field with space in between valid input | 1. Browse the URL ("https://www.zappos.com/") 2. Put the number with space 4. Click on the Registration butto | Phone: 015 56789 | User should not be able to registration and there should be an alert such as "Please fill retype password" | Not able to registration and the alert message shows properly |  | Passed
TC014 |  |  | Tey to registration Phone field with already existed phone number | 1. Go to url "https://www.zappos.com/" 2. Click on "registration" button. 3. Put test data on phone field 4. Click on registration button | phone: 01623****14 | User should not be able to registration and there should be an alert such as "Please fill retype password" | Not able to registration and the alert message shows properly |  | Passed
TC015 |  |  | Try to registration Password field with alphabets | 1. Go to url "https://www.zappos.com/" 2. Click on "login" button. 3. A new page will appear having Registration In and registration button. Click on "Registration" button 4. put test data on password field | Password: ramisajgfdh | User should be able to registration | able to registration |  | Passed
TC016 |  |  | Try to registration password does not take more than 20 digit | 1. Go to url "https://ajkerdeal.com" 2. Click on "login" button. 3. A new page will appear having Registration In and registration button. Click on "Registration" button 4. put test data on password field | Password: ramisa@7890987654321# | User should not be able to registration | System take mora then 20 digit and User able to registration |  | Failed
TC017 |  |  | Try to registration Password field with numbers | 1. Go to url "https://www.zappos.com/" 2. Click on "login" button. 3. A new page will appear having Registration In and registration button. Click on "Registration" button 4. put test data on password field | Password: 368236484787 | User should be able to registration | User able to registration |  | Passed
TC018 |  |  | Try to registration Password field with space inputs | 1. Go to url "https://ajkerdeal.com" 2. Click on "login" button. 3. A new page will appear having Registration In and registration button. Click on "Registration" button 4. put test data on password field | Password: 47123 678 | User should not be able to register | User able to registration |  | Failed
TC019 |  | login | Try to login Email field with empty input | 1. Go to url "https://www.zappos.com/" 2. Go to "login" menu and click on login 3.keep mail field emty 4.click on login button | mail: Null | User should not be able to login and show error massage | Not able to login the alert message shows properly |  | Passed
TC020 |  |  | Try to login Email field with invalid format | 1. Go to url "https://www.zappos.com/" 2. Go to "login" menu and click on login 3.Put mail invalid formate 4.click on login button | Mail: (ramisa12hjhi@gmail.com | User should not be able to login and show error massage | Not able to login the alert message shows properly |  | Passed
TC021 |  |  | Try to login Email field with numbers | 1. Go to url "https://www.zappos.com/" 2. Go to "login" menu and click on login 3.put mail only number 4.click on login button | Mail: 2089847697450 | User should not be able to login and show error massage | Not able to login the alert message shows properly |  | Passed
TC022 |  |  | Try to login Email field with only alphabets | 1. Go to url "https://www.zappos.com/" 2. Go to "login" menu and click on login 3.Put mail formate only alphabet 4.click on login button | Mail: thkjhfsdjhjhhkdfjgkdfj | User should not be able to login | Not able to login the alert message shows properly |  | Passed
TC023 |  |  | Try to login Email field with already existed mail id | 1. Go to url "https://www.zappos.com/" 2. Go to "login" menu and click on login 3.Put mail invalid formate 4.click on login button | Mail: ajSQA2987@gmail.com | User should not be able to login and show error massage | Not able to login the alert message shows properly |  | Passed
TC024 |  |  | Try to login Email field without " @ " sign | 1. Go to url "https://www.zappos.com/" 2. Go to "login" menu and click on login 3.Put mail without @ sign 4.click on login button | Mail: Hi.cdjfhj.gmail.com | User should not be able to login | Not able to login the alert message shows properly |  | Passed
TC025 |  |  | Try to login Password field empty | 1. Go to url "https://www.zappos.com/" 2. Go to "login" menu and click on login 3.Keep password field emty 4.click on login button | mail :afr.bgjsf.@gmail.com password:Null | User should not be able to login and show error massage | Not able to login the alert message shows properly |  | Passed
TC026 |  |  | Try to login Password field with alphabets | 1. Go to url "https://www.zappos.com/" 2. Go to "login" menu and click on login 3.put password formate only alphabet 4.click on login button | Password:jaytfhj | User should be able to login | able to login |  | Passed
TC027 |  |  | Try to login Password field with special characters | 1. Go to url "https://www.zappos.com/" 2. Go to "login" menu and click on login 3.Put password formate with special carecter 4.click on login button | Password: ajgdtagyt$#@ | User should be able to login | able to login |  | Passed
TC028 |  |  | Password field with space inputs | 1. Go to url "https://www.zappos.com/" 2. Go to "login" menu and click on login 3.Put password with space 4.click on login button | Password:@yjkj.agyt *** | User should not be able to login and show error massage | Not able to login the alert message shows properly |  | Passed
TC029 |  |  | Try to login Maximum password length 11 digit | 1. Go to url "https://www.zappos.com/" 2. Go to "login" menu and click on login 3.Put password 4.click on login button | password :05345648906 | User should not be able to login with morethan 11 carecter | User use more than 11 character |  | Failed
TC030 |  |  | Try to login valid email but invalid password | 1. Go to url "https://www.zappos.com/" 2. Go to "login" menu and click on login 3.Put invalid password and invalid email 4.click on login button | Email:ramisahjfhr@gmail.com password:$#^&*($#@ | User should not be able to login and show error massage | Not able to login the alert message shows properly |  | Passed
TC031 |  |  | Try to login with valid email and valid password | 1. Go to url "https://www.zappos.com/" 2. Go to "login" menu and click on login 3.Put valid password and valid email 4.click on login button | Email:ajjfhr@gmail.com password: jafor3586789 | User should be able to login | user login properly |  | Passed
TC032 |  |  | Try to login without email and password | 1. Go to url "https://www.zappos.com/" 2. Go to "login" menu and click on login 3.kepp password and email emty 4.click on login button | Email:Null password:Null | User should not be able to login and show error massage | Not able to login the alert message shows properly |  | Passed
TC033 |  | Order | Verify L.L.Bean Product menu show | 1.Brows Url 2.click one by one product menu |  | Produt menu should be available | Product menu working fine |  | Passed
TC034 |  |  | Verify that user should be able to order the product with proper schole bage information and step. | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping 6.Select Home town 7.select payment option 8.Selact delivery system 9. Click order confrom |  | user should order properly | user order properly |  | Passed
TC035 |  |  | Verify that on the product page, the user can select the desired attribute of the product e.g. size, color, etc. | 1.Click product Images 2.Select size |  | User shoud be able select Size with radio button | User able to select size properly |  | Passed
TC036 |  |  | Verify that the user can add to cart one or more products. | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping 6.Select Home town 7.select payment option on card 8.Selact delivery system 9. Click order confrom |  | user should order properly with cart | user order properly |  | Passed
TC037 |  |  | verify user select size more than one at a time | 1.Click product Images 2.Select size |  | User should not selet more than size ta a time | User not select more than one size |  | Passed
TC038 |  |  | Verify that users can add more products to the list | 1.Click product Images 2.Select size 3. Again go home and select product |  | User should be add more than one product | User able to add more product properly |  | Passed
TC039 |  |  | Verify that the user can not be add more than the available inventory of the product. | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping 6.Select Home town 7.select payment option 8.Selact delivery system 9. Click order confrom |  | User should be cannot add more than one product | User able to add more product properly |  | Failed
TC040 |  |  | Verify that the limit to the number of products a user can by is working | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping 6.Select Home town 7.select payment option 8.Selact delivery system 9. Click order confrom |  | User should be order product number of limit | User can order product number of limit |  | Passed
TC041 |  |  | Verify that the different items in Cart methods of adds are working fine. | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping 6.Select Home town 7.select payment option 8.Selact delivery system 9. Click order confrom |  | User can be different items products add properly. | Different items products shoud be add properly. |  | Passed
TC042 |  |  | Verify that product remove functionality works fine. | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping 6.Select Home town 7.select payment option 8.Selact return option 9. Click return confrom |  | Product return function should working fine | Product return function working well |  | Passed
TC043 |  |  | Verify that user should be able to return the order after delivery of order. | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping 6.Select Home town 7.select payment option 8.Selact remove option 9. Click remove confrom |  | should be able to return the order after delivery of order. | able to return the order after delivery of order. |  | passed
TC044 |  |  | Verify that user should be able to exchange the order from My orders page. | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping 6.Select Home town 7.select payment option 8.Selact exchange option 9.confrom exchange |  | should be able to exchange the order from My orders page | able to exchange the order from My orders pag |  | Passed
TC045 |  |  | Verify the searching work properly | 1.go home page 2.write product name or category 3.click search button |  | user should be search product properly | user can search product properly |  | Passed
TC046 |  |  | Verify that the view cart option of working fine. | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping |  | User view cart option should be work properly | check in view cart option working properly |  | Passed
TC047 |  |  | Verify the product in checkout work properly | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping |  | User show product in checkout option view properly | product in checkout option work properly |  | Passed
TC048 |  |  | Verify the free shipping and returns 365 days to return items for a refund work properly | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping |  | User can be free shipping and returns 365 days to return items for a refund. | Check in view free shipping and retun option working properly |  | Passed
TC049 |  |  | verify order product without Address | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping 6.Select Home town |  | order product without Address should not working | not working system show an error massage |  | Passed
TC050 |  |  | verify order with cash on delivery | 1.Click product Images 2.Select size 3.Place order button 4.Click purches button 5.Click end step of shoping 6.Select Home town |  | Order sucessfully but not add deel properly. | Order sucessfully but not add deel |  | Passed
TC051 |  | Address Shipping | Verify to shipping address | 1.Click on shipping address 2.Select cuntry state. 3.Fill in name option | Country: USA. Full name: Ramisa Anan | User should be able to country option. | User should be able to country select option properly . |  | Passed
TC052 |  |  | Verify to address line | 1.Fill in address line-1 2.Fill in address line-2 | Address line-1: fsayty% Address line-2: Nasa3@ | User should be able to address . | User should be able to address properly . |  | Passed
TC053 |  |  | Fill up in city, state, zip | 1.Click on Shipping address. 2.Fill in city. 3.fill in stat 4.Fill in zip. 5.Fill in phone no. | City: SAdy. State: Fsew1. Zip:23s4 | User should be able to city, state, zip . | User should be able to address shipping properly. |  | Passed
TC054 |  | Payment | Verify Payment with Credit card. | 1.brows url 2.click on login option 3.loding new page for sign in 4.order product 5.click on bkash option |  | User should be Payment sucessfully | User Payment sucessfully |  | passed
TC055 |  |  | Verify Payment with Amazon pay. | 1.brows url 2.click on login option 3.loding new page for sign in 4.order product 5.click on marchent account option |  | User should be Payment sucessfully | User Payment sucessfully |  | passed
TC056 |  |  | Verify Payment with paypal | 1.brows url 2.click on login option 3.loding new page for sign in 4.order product 5.click on Visa card Option |  | User should be Payment sucessfully | User Payment sucessfully |  | passed
TC057 |  |  | Verify Payment with afterpay. | 1.brows url 2.click on login option 3.loding new page for sign in 4.order product 5.click on Visa card Option |  | User should be Payment sucessfully | User Payment sucessfully |  | passed
TC058 |  | Credit Card | Try to fill up without first,last name on card | 1.Brows Url 2.click name on card option 4. click to button with value. |  | User should be able an alert such as "Please enter Name on card". | Able to the alert message shows properly |  | Passed
TC059 |  |  | Fill in first name, last name with accept Alpabetic and numeric number on card | 1.Brows Url 2.click name on card option 4. click to button with value. 5. abu32b, jaor23 | First,last name: Ramisa3, An6guy2 | User should not be able an alert such as "Please enter Name on card". | User should not be able an alert such as "Please enter Name on card". | Name and Card number issue | Failed | Card number issue
TC060 |  |  | Try to Add payment enter number and Wiithout numeric valu field emty | 1.Brows Url 2.click on Marchent Corner option 3.loding a page for registration and login 4. Fill up Buisness name and phone number 5.click registration button without value | Add payment: enter number Enter card no:01376874638 enter no : Null | User should be able enter card number and there should be an alert such as "Please enter numeric number " | Not able to enter card number and the alert message shows properly |  | Passed
TC061 |  |  | Try to Expiry date on add payment option | 1.Brows Url 2.click on expiry date button. | Expiry date: numeric characters MM/YY:05/11 | User should be able toregistration and there should be an alert such as "Please enter Numeric value" | Not able to the alert message shows properly |  | Passed
TC062 |  |  | Fill in enter card number only alphabetic value | 1.Brows Url 2.click on card number option 4.click on button without value | Add payment: Card number No:shdhhdui123bf | User should not be able Card number and there should be an alert such as "Please enter numeric number " | Not able to card number and the alert message shows properly |  | Passed
TC063 |  |  | Try to card varification value | 1.Brows Url 2.click on CVV option 3.fill up option | CVV: Number: 65743564658 Phone:Null | User should be able to CVV there should be an alert such as "Please enter CVV number " | CVV code shows properly |  | Passed
TC064 |  |  | Try to CVV code with OTP Code | 1.Brows Url 2.click on CVV option 3.fill up option 4.click CVV button value | Buisness: Name: 65743564658 Phone:01516144938 facebook link : https://www.facebook.com/ | User be able to CVV with OTP code. | System provide OTP code |  | Passed |  | 1. Name field should take only text input or combination of text, numeric.
TC065 |  |  | fill up in Add payment option with proper information | 1.Brows Url 2.click on enter option 4.fill up option 4.click on Add payment button with value | Buisness: Name: 65743564658 Phone:01516144938 facebook link : https://www.facebook.com/ | User should be able to registration . | User should be able to registration . |  | Passed |  | 2. Tab button should work for navigating for every field, checkbox, hyperlink and button
TC066 |  | Forget Password | Try to reset password from option and puting valide phone number | 1.Brows Url 2.click on login option 3.Fill email Option 4. click forget password button |  | System should be provide OTP code | System Doesn't provide OTP code |  | Passed
TC067 |  |  | Try to reset password from option and puting phone number | 1.Brows Url 2.click on login option 3.Fill email Option 4. click forget password button |  | System should be provide OTP code | System Doesn't provide OTP code |  | Failed
|  | Woman Shose | Verify the product All Shop shose | [5 empty] | Out of Scope

## Test report
Test Case Report
Project Name - | https://www.zappos.com/
Module Name - | User Management web page |  |  |  |  | Total No. | Status | Result :
Test Case Version | - |  |  |  |  | 59 | PASS
Written By | Ramisa Anan |  |  |  |  | 8 | FAIL
Executed By | Ramisa Anan |  |  |  |  | 0 | Not Executed | New Features | Testing Scope | Testing Environment :
Reviewed By | [5 empty] | #ERROR! | Out of Scope |  |  | Test Environment | Google Chrome Browser
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 59 | 8 | 0 | #ERROR! | 67
Grand Total | 59 | 8 | 0 | #ERROR! | 67
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of (“attitude to break”) using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting | Bug Report
TC:059 | TC:059
Issue: Name issue Numeric and Alphabet value accepet | Issue: unstructured Card number
Reproducing Steps: | Reproducing Steps:
1.Brow Url | 1.Brows Url
2.Select Name and Card number Option | 2.click on enter card number option
3.Click on Full Name | 3.Fillup card number option
3.keep password
Env: | 4.Click on Add payment button show invalide
Module: Add Payment | Env:
Severity:P1 | Module: Payment card
Screenshot: https://drive.google.com/file/d/19dWk6-xdCU21b2UIWjynuPryddTWveXE/view?usp=sharin | Severity:P3
Responsible QA: Ramisa Anan | https://drive.google.com/file/d/19dWk6-xdCU21b2UIWjynuPryddTWveXE/view?usp=sharing
| Responsible QA: | Ramisa Anan)

## Test matrix
Test Metrics
SL NO | Metrics | Description | Result
1 | Percentage of test cases Executed | (No.of Test Cases Executed / Total no.of Test Cases Written)*100 | (67/67)*100 = 100
2 | Percentage of test cases not Executed | (No.of Test Cases not Executed / Total no.of Test Cases Executed)*100 | (0/67)*100 = 0
3 | Percentage of test cases Passed | (No.of Test Cases Passed / Total no.of Test Cases Executed)*100 | (59/67)*100 = 88.05
4 | Percentage of test cases Failed | (No.of Test Cases Failed / Total no.of Test Cases Executed)*100 | (08/67)*100 = 11.94
5 | Percentage of test cases Blocked | (No.of Test Cases blocked / Total no.of Test Cases Executed)*100 | (0/67)*100 = 0
6 | Defect Density | No. of defect found / Size (No.of requirments) | N/A
7 | Defect Removal Efficiency(DRE) | (Fixed Defects / (Fixed Defects + Missed Defects))*100 | N/A
8 | Defect Leakage | (No of Defects found in UAT / No.of Defects found in Testing)*100 | N/A
9 | Defect rejection Ratio | (No.of Defects Rejected / Total no.of Defects raised)*100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No.Of complaints per Period of Time | N/A